## Slide 1
TELECOM CYBER PORTFOLIO
CONFIDENTIAL / 2026
01
Executive Review
Telecom Cyber Portfolio
| Executive Review
Cyber delivery is funded, but schedule risk is concentrated
in the integration-heavy work.
PORTFOLIO SNAPSHOT | 2026
10 projects • $2.83M budget • 75.6% average milestone completion

## Slide 2
TELECOM CYBER PORTFOLIO
CONFIDENTIAL / 2026
02
PORTFOLIO OVERVIEW
A funded portfolio with a split health picture
ACTIVE CYBER PROGRAMS
10
10 active cyber security
projects
DELIVERY HEALTH
4
On Track
3
Delayed
3
At Risk
4 On Track | 3 Delayed | 3 At Risk
FINANCIAL POSITION
$2.83M
budget
$2.79M actual spend
Portfolio spend is $40K under
budget (−1.4%)
PORTFOLIO
HEALTH
Management signal: cost is controlled, but delivery is not
The RAG split and milestone gaps point to execution exposure rather than funding
pressure.

## Slide 3
TELECOM CYBER PORTFOLIO
CONFIDENTIAL / 2026
03
SCHEDULE PERFORMANCE
Schedule exposure is concentrated
in transformation projects
AVERAGE MILESTONE
COMPLETION
75.6%
Against a 100% planned
milestone baseline across
the portfolio.
LARGEST GAPS SHOWN
AT RIGHT
ACTUAL COMPLETION BY PROJECT
100% PLAN
Cloud Security Assessment
60.0% complete (−40.0 pts vs plan)
SIEM Migration
63.8% complete (−36.2 pts)
DDoS Protection
65.0% complete (−35.0 pts)
Privileged Access Management
66.2% complete (−33.8 pts)
The critical path is slowing where integrations, vendors and specialist skills converge

## Slide 4
TELECOM CYBER PORTFOLIO
CONFIDENTIAL / 2026
04
FINANCIAL EXPOSURE
Underspend is masking delivery slippage
DELAYED-PROJECT VARIANCE
+$70K
Delayed projects are collectively
$70K over budget
PORTFOLIO TOTAL
−$40K
Portfolio total is still $40K under
budget
DELAYED PROJECT COST VARIANCE
BUDGET IMPACT
DDoS Protection
+$30K | +9.4%
Cloud Security Assessment
+$25K | +16.7%
NextGen Firewall Upgrade
+$15K | +6.0%
Portfolio total is still $40K
under budget because several
projects are underspending
while behind plan
Treat underspend as
unconsumed delivery, not
savings

## Slide 5
TELECOM CYBER PORTFOLIO
CONFIDENTIAL / 2026
05
RISK AND ISSUE CONCENTRATION
Risk is clustered around
integration and capacity
PORTFOLIO RISK REGISTER
15
15 risks logged
7
critical score-9 risks
11
open
Integration
Legacy log-source
integration and PAM
compatibility are
critical exposures.
Capacity
SOC and cloud
security specialist
shortages are
slowing execution.
Vendor
Firewall and DDoS
deployment
dependencies
require escalation.
STEERING PRIORITIES
Top steering priorities: legacy
log-source integration
SOC engineering capacity
DDoS vendor deployment
Mitigation pattern: add
specialist capacity, prioritize
critical integrations, and
escalate vendors weekly
Risk owners: CISO, SOC Manager, SIEM Manager,
Vendor Manager
OPEN EXPOSURE REQUIRES
ACTION

## Slide 6
TELECOM CYBER PORTFOLIO
CONFIDENTIAL / 2026
06
MANAGEMENT ACTION
Three decisions to restore delivery confidence
01
Stabilise delayed programs:
sponsor vendor escalations,
backup suppliers and protected
test environments
02
Protect the SOC/SIEM critical
path: add specialist capacity
and prioritize critical log
sources
03
Turn the portfolio into an
early-warning system: weekly RAG
review with triggers at <90% of
plan, risk score ≥9, or cost
variance >5%
DECISION REQUESTED
approve targeted capacity and vendor intervention now — before
delays become operational exposure
Telecom Cyber Portfolio | Executive Review
Source: supplied project, milestone, financial and risk register data

## Slide 7
TELECOM CYBER PORTFOLIO
TASK 4 / PROCESS DESIGN
07
TASK 4 | PROCESS AND WORKFLOW DESIGN
Tracking Cyber Project Progress & Reporting
A controlled weekly loop from source data to stakeholder action — with validation before
anything reaches the dashboard.
01
Data collection
PMs update MySQL
tables: Projects,
Milestones, Tasks,
Risks_Issues and
Resources.
OWNER: PM / PMO
→
02
Validate & approve
BA checks completeness,
dates, Planned % vs
Actual %, status, cost
variance and risk scores.
GATE: APPROVE OR
RETURN
→
03
Export & dashboard
update
Export validated MySQL
tables to dated CSV,
refresh Power BI Power
Query, then confirm RAG,
schedule, financial and
risk visuals.
CONTROL: REFRESH
CHECK
→
04
Stakeholder
reporting
Share the dashboard and
executive summary with
CISO, sponsors and PMs;
capture decisions and
actions.
OUTPUT: ACTION LOG
Exception loop: failed validation or refresh → return to owner →
correct source data → revalidate → re-export → refresh again
WEEKLY CUT-OFF: THURSDAY
DASHBOARD REFRESH: FRIDAY
STEERING REVIEW: MONDAY